## Sheet1
Serial | Task | Category | Priority | EstimateEnd Date | Status | Reamarks
1 | Delegation in self service |  | 1 | 2025-01-09 | Done | Sunday 12-01-2025 will be published
2 | Sending E-Mail |  | 1 |  | InProgress | Still Check With Eng Abdulsalam
3 | Employee File history Form |  | 2 | 2025-01-14 | Done | Sunday 12-01-2025 will be published
4 | Cancel Request in self service |  | 3 |  |  | Phase 2
5 | Arabic language issue Issue on server |  | 4 |  |  | to Check With Eng Abdulsalam
6 | Annual vacation balance |  | 5 |  |  | need 3 week to add the 2025 balance
7 | Self-Service Training Video |  | 6 | 2025-01-09 | Done | Will be Sent after today meeting
8 | Bank Account Update Request in self service Add Old data and empty field for new data |  | 7 | 2025-01-15
9 | Contact Information Update Request in self service Add Old data and empty field for new data |  | 8 | 2025-01-15
10 | Employee File Update Request in self service Add Old data and empty field for new data |  | 9 | 2025-01-15
11 | In Self-Service Send E-mail to the requester with each action |  | 10 |  |  | Phase 2
12 | Openening Vacancies Report |  | 11 | 2025-01-20
13 | Attached Document Report |  | 12 | 2025-01-20 | Done | but we need to have the same report that you sent before
14 | End of service raquest Reasons |  | 13 | 2025-01-20
15 | Excuse Hours To be maximum 4 hours |  | 14 | 2025-01-20
16 | in Dash board Add turnover chart |  | 15 |  |  | Will check availability
17 | Fingerprint Attendnce |  | 16 |  |  | Dataocean are ready waiting for it department to finish installing machines
18 | Forgot Password |  | 17 |  |  | phase 2
19 | Recruitment Module |  | 18 |  |  | phase 2
20 | Appresal Module |  | 19 |  |  | phase 2
21 | Separate Additions and deduction forms |  | 5 |  |  | phase 2